# Data Project Lifecycle

## Summary

The primary intent of this document is to establish a formal, gated delivery standard for data projects. By focusing on the Data Project Lifecycle—particularly the initial stage of Data Product Definition—it ensures that each project aligns scope, business value, and acceptance boundaries through explicit documentation of use cases, consumers, and service level agreements. This approach provides structured criteria for project initiation, including business owner identification, KPIs, and source systems, thereby promoting clarity, accountability, and controlled progression at every stage.

# Stage 0 — Data Product Definition

Purpose: Align scope, business value, and acceptance boundaries. Makes use case, consumers and SLA’s/OLA’s explicit

Inputs

- Use case / regulatory requirement / MI ask (documented)

Outputs / Evidence

- Data Product Brief: decisions supported, primary KPIs, consumers, refresh SLA, critical dimensions, data owner

Exit criteria (DoD)

- Business owner named for acceptance

- KPIs named (even if not fully specified yet)

- Source systems list

- “In-scope entities & subject areas” and defined at high level

- SLA’s/OLA’s clearly defined

- Quality and Reconciliation approach defined

# Stage 1 — Data Mapping

Purpose: Translates Business meaning to Data logic. Removes ambiguity before modeling/engineering. Prevents later “semantic drift” and BI logic invention

Inputs

- Product brief

- Source system list

Outputs / Evidence

- Source→target mapping, KPI definitions, transformation rules, reconciliation approach

Exit criteria (DoD)

- KPI definitions written in business language and approved by business owner

- Mapping signed off by Data Product Owner(s) + Data Architecture

- Reconciliation logic explicitly agreed

# Stage 2 — Source Feasibility & Inventory Gate

Purpose: Validate scope and physical realities before modeling/DDL work.

Inputs

- Mapping draft (Stage 1)

- Access to source / existing prod DDLs

Outputs / Evidence (explicit)

- Authoritative Table Inventory for the initiative (Silver + Gold where relevant)

- Confirmed “in-scope tables” list (subject areas + counts)

- Known constraints log (latency, history gaps, code table issues)

Exit criteria (DoD)

- In-scope table list reconciled with production reality (not estimates)

- Any discrepancy between “assumed” and “actual” scope is resolved or formally accepted

# Stage 3 — Data + Physical Design Gate

Purpose: Ensure the model is not “80% complete”—it is buildable and enforceable.

Inputs

- Signed mapping (Stage 1)

- Confirmed table inventory (Stage 2)

Outputs / Evidence

A) Logical model updates (entities, grain, conformance)
B) Physical model standards applied (keys, datatypes, naming)
C) Modeler-approved DDL (or generated from the model) for the in-scope tables
D) Schema standards checklist (PK/FK, datatypes, naming convention, surrogate keys)

Exit criteria (DoD)

For every in-scope table:

- Primary Key defined in the model AND implemented in DDL

- Foreign Keys defined where applicable and implemented (or explicitly waived with rationale)

- Datatypes are defined (not default “all string”)

- Naming standard applied (case + convention)

- Surrogate key policy applied (defined or explicitly not needed)

“No DDL is ‘approved’ until it passes the schema standards checklist.”

# Stage 4 — Data Engineering Build + DDL Change Control Gate

Purpose: Build pipelines only against approved schemas; prevent uncontrolled schema drift.

Inputs

- Modeler-approved DDL (Stage 3)

- Versioned mapping + transformation rules

Outputs / Evidence

- Bronze→Silver→Gold pipelines

- Data tests (row counts, null constraints, key uniqueness checks)

- Deployment scripts and environment promotion plan

Exit criteria (DoD)

- Pipelines run end-to-end in Dev with repeatable outputs

- DDL execution performed only using modeler-reviewed DDL (hard control)

# Stage 5 — Data Quality Validation (Reconciliation Gate)

Purpose: Prove correctness, not just “pipeline runs”.

Inputs

- Pipeline outputs from Stage 4

- Reconciliation rules from Stage 1

Outputs / Evidence

- DQ scorecard (completeness, consistency, validity, timeliness)

- Reconciliation results vs sources

- Exception register with business acceptance

Exit criteria (DoD)

- Reconciliation within agreed thresholds OR exceptions explicitly accepted

- Key integrity checks pass (PK uniqueness; FK referential integrity where implemented)

# Stage 6 — Logical Mart Review & Sign-off (Data Acceptance Gate)

Purpose:
Business signs off the data product, not visuals. Confirms semantic correctness & decision fitness.

### Inputs

- DQ scorecard

- Data dictionary & metric definitions

- Lineage artefacts (logical → physical → source)

- Production-representative datasets or justified proxy

### Outputs / Evidence

- Business sign-off for mart readiness

- Confirmed “data is fit for purpose”

- Decision coverage matrix (KPIs → business/regulatory decisions)

- Data lineage attestation (KPI → Gold → Silver → source)

- Exception register with owner, rationale, and review expiry

### Exit criteria (DoD)

- Business owner signs off on dataset + KPI correctness

- Each KPI mapped to at least one explicit decision scenario

- Lineage verified end-to-end with no semantic logic introduced post-model

- Data validated on production-representative volumes (or proxy accepted)

- All quality or reconciliation exceptions have named business owners

- Dataset is defensible to Audit / Risk / Regulator where applicable

# Stage 7 — Semantic / Report Build (incl. RLS) (Consumption Gate)

Purpose: Build semantic models without redefining business logic, while enforcing access control, performance, and consumption governance.

Inputs

- Signed mart (Stage 6)

- Approved KPI definitions and lineage

Outputs / Evidence

- Power BI semantic model, measures, RLS documentation

- Semantic parity checklist (Gold logic vs BI definitions)

- RLS persona definitions and test results

- Performance and scale validation results

- Semantic versioning and dependency register

Exit criteria (DoD)

- No KPI logic exists only in BI (proved via parity check)

- All measures trace directly to Gold/mart logic

- RLS defined using business personas, not report logic

- RLS tested for positive and negative scenarios (incl. join leakage)

- Semantic model performance validated for expected concurrency/volume

- Versioning and backward-compatibility impact understood and signed off

- All consuming reports, extracts, APIs have named owners

# Stage 8 — UAT (Usage Validation Gate)

Purpose: Validate decision correctness and usability, not just visual accuracy.

Inputs

- Semantic layer ready

- Business test scenarios

- Near-final datasets

Outputs

- UAT results mapped to business scenarios

- Defect and exception log with business severity

- Re-run reconciliation results on pre-go-live data

- Formal decision-level acceptance

Exit criteria (DoD)

- UAT completed using scenario-based testing (normal + boundary cases)

- Negative tests executed (invalid dimensions, access violations, edge dates)

- Reconciliation checks repeated with no unexplained drift

- Business confirms:
“I would take the intended decision using this data without alternate spreadsheets.”

- Accepted variance thresholds and post-go-live tolerance declared

- Named ownership for post-go-live data issues agreed

# Stage 9 — Production Readiness (Run/Operate Gate)

Purpose: Ensure operability and control.

Inputs

- UAT sign-off

Outputs

- Monitoring & alerting configured

- Runbook (support model, escalation)

- Access controls implemented

Exit criteria (DoD)

- SLA, monitoring, ownership defined

# Stage 10 — Go-live / Hypercare (Stabilization Gate)

Purpose: Stabilize and transition to BAU.

Inputs

- Prod readiness signed

Outputs

- Hypercare logs, post-go-live report

- KT complete

Exit criteria (DoD)

- BAU ownership acceptance